# Project Charter

Project Title: Case Studies to Video Generator

Date: January 19, 2026

## 1. Executive Summary

A high-level snapshot of who is doing what and when. This project aims to deploy a fully automated pipeline that converts static text PDFs into dynamic 64-second videos using AI orchestration and browser automation.

| Role | Who | Start Date | End Date |
| --- | --- | --- | --- |
| Responsible (Owner) | Group 7 | Day 1 | Day 6 |
| Data and Automation Engineer | Shruti Gupta, Vaishnavi Zope, Vishwa Pethani | Day 1 | Day 6 |
| Marketing and Content Executive | Pratik Motwani | Day 1 | Day 6 |

## 2. Purpose

### 2.1 Project Background (The "Why")

Context: Currently, converting a written case study into a video asset requires manual scriptwriting, storyboard creation, and video editing.

Problem: This manual process is time-consuming and creates a bottleneck in our content marketing pipeline.

Opportunity: By leveraging n8n for orchestration and BrowserUse for interacting with generative video tools (Flow AI), we can reduce production time to near-zero human effort.

### 2.2 Project Objective (The "Goal")

Objective: Develop a locally-hosted automated workflow that monitors a Google Drive folder for input assets (PDF + 2 Logos) and converts them into a 64-second video.

Key Technical Requirement (The "3-Layer Prompt"):

The system must generate prompts that explicitly combine three distinct layers for every scene:

- Global Style Token: A merged string containing:

  - Static: Our Company's Theme Guidelines (Stored locally/static).

  - Dynamic: Case Study Company's Theme (Extracted via LLM).

  - Atmospheric: Lighting, Tone, Camera Angle.

- Visual Template: Defines spatial layout (e.g., "Our Logo bottom-left", "Client Logo top-right", "Text overlay top-center").

- Scene Action: The specific visual narrative for that 8-second segment.

### 2.3 Customer Benefit (The "Value")

- Marketing Team: Saves ~5 hours of manual work per video asset.

- Brand Consistency: Ensures every video follows the exact same "Style Token" and "Visual Template" via the new Brand Guardian agent.

### 2.4 Technical Workflow (Process Logic)

The automation must strictly follow this sequential flow:

- User Input: User uploads 3 files to a specific Google Drive folder: Case Study PDF, Company Logo (PNG), and Client Logo (PNG).

- Prompt Generation: n8n fetches the files. It reads the PDF and uses an LLM to generate 8 distinct "Scene Prompts."

- Parallel Theme Extraction: Simultaneously, n8n uses an LLM to extract the "Client Company Theme" from the PDF.

- Static Asset Retrieval: n8n retrieves the static "Our Company Theme" and "Visual Template" definitions.

- Combination & Verification: n8n merges the [Global Style Token + Visual Template + Scene Prompt] into 8 final prompt strings. The Prompt Auditor Agent then cross-verifies these final strings against the brand guidelines.

- Payload Handoff: n8n sends the 8 verified prompts and the 2 logo file paths to the BrowserUse script.

- Browser Execution: The BrowserUse agent (Python) logs into Flow AI and inputs each prompt one by one.

- Video Capture: BrowserUse waits for generation and saves the finished video file.

- Delivery: The final video is uploaded back to the same Google Drive folder for user review.

## 3.1 Work Breakdown Structure (WBS) & Roadmap

This timeline is strictly compressed to a 6-day sprint.

| WBS ID | Task/Milestone Name | Task Type | Dependency | Responsible | Start | End | Deliverable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 | MILESTONE: Logic & Agents Implementation | Sequential | - | Group 7 | Day 1 | Day 3 | Verified Prompts |
| 1.1 | Project Planning & Environment Setup (Local) | Sequential | - | Shruti Gupta | Day 1 | Day 1 | Approved Charter |
| 1.2 | n8n Setup: Google Drive Trigger & Asset Parsing | Sequential | 1.1 | Vishwa Pethani, Vaishnavi Zope | Day 1 | Day 2 | Drive Watcher Node |
| 1.3 | Parallel Agents: Theme Extraction & Static Retrieval | Sequential | 1.2 | Pratik Motwani (Logic), Shruti (Dev) | Day 2 | Day 2 | Global Token JSON |
| 1.4 | Scene Prompt Agent: Generation | Sequential | 1.3 | Pratik Motwani | Day 2 | Day 3 | 8 Raw Scene Prompts |
| 1.5 | Prompt Combination & Auditor Agent | Sequential | 1.4 | Vishwa Pethani, Vaishnavi Zope | Day 3 | Day 3 | 8 Verified Final Prompts |
| 2.0 | MILESTONE: Browser Automation & Integration | Sequential | 1.5 | Group 7 | Day 4 | Day 6 | Working Prototype |
| 2.1 | Python Browser Agent: Flow AI Interaction | Sequential | 1.5 | Vaishnavi Zope | Day 4 | Day 5 | Working Script (Local) |
| 2.2 | Integration: Connect n8n Agents to Python Script | Sequential | 2.1 | Shruti Gupta | Day 5 | Day 5 | End-to-End Flow |
| 2.3 | User Acceptance Testing (UAT) | Sequential | 2.2 | Pratik Motwani | Day 6 | Day 6 | UAT Feedback Log |
| 2.4 | Final Code Refinement & Buffer | Buffer | 2.3 | Group 7 | Day 6 | Day 6 | Final Local Codebase |

### 3.2 Flowchart:

.

## 4. Project Details

### 4.1 Scope (In vs. Out)

In Scope:

- Input Trigger: Google Drive Folder Watcher (Must detect 3 files: 1 PDF Case Study, 1 Company Logo PNG, 1 Client Logo PNG).

- Advanced Workflow: Includes "Brand Guardian" (Token/Template generation) and "Prompt Auditor" (Compliance check) agents.

- Output: Final Video uploaded back to the Google Drive Output folder.

Out of Scope:

- Video Editing: No post-production (music syncing, voiceover adjustments).

- Public Access: The tool will only be accessible to the developer running the localhost server.

### 4.2 Budget

- Software Subscriptions:

  - Google AI Pro Plan (Incl. 1000 Monthly Credits): ~₹1950/month

  - n8n: Free (Self-hosted Desktop Version).

- Labor: Internal Developer hours.

### 4.3 Resources

- People:

  - Data and Automation Engineers: Shruti Gupta, Vaishnavi Zope, Vishwa Pethani

  - Marketing and Content Executive: Pratik Motwani

- Tools:

  - Storage/Trigger: Google Drive (Shared Folder).

  - Orchestration: n8n (Desktop Version).

  - AI Logic: Google Gemini.

  - Browser Agent: browser-use Python library + Headless Chromium.

- Infrastructure: Local Development Machine (High RAM required for running Browser + n8n + AI).

### 4.4 Risks

| Risk Description | Impact | Mitigation Strategy |
| --- | --- | --- |
| Input Asset mismatch: User uploads PDF but forgets the logos, or names them incorrectly. | High: Workflow fails to generate the "Visual Template." | Mitigation: Add an n8n logic node that checks for all 3 files before starting. Send an error alert if files are missing. |
| Agent Complexity: Adding two extra agents (Guardian & Auditor) increases latency and error points. | High: Workflow might timeout or become too slow. | Mitigation: Run agents in parallel where possible, or use "Flash" models for the Auditor agent to save time. |
| Flow AI UI Changes: The video generation site changes its button layout. | Critical: Script failure. | Mitigation: Hardcode selectors for the specific 6-day sprint duration; worry about robustness in Phase 2 |

### 4.5 Communication Plan

- Daily Stand-up: 10-min sync every morning (Days 1-6).

- Immediate Bug Reporting: Direct message in Group Chat for any blocker.

### 4.6 Final Success Measurement

The project is considered complete when:

- The "Brand Guardian" successfully extracts a Style Token and merges it with the 2 Logo assets.

- The "Prompt Auditor" successfully approves valid prompts and rejects invalid ones.

- We have generated 3 consecutive videos locally using the 3-file input method without manual intervention.

### 4.7 Future Plans & Sustainability

- Phase 2 (Priority):

  - Application Scaling: Enable generation of 2-3 minute videos.

- Phase 3:

  - Automation tool to be able to post the Youtube videos with appropriate title and description.